## Electrical
Task | Subsystem | Priority (0 is highest) | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
ROS 2 Rover Architecture |  | P1 | Youssef Gabriel Amazirh | In progress | 2025-12-21
|  | P1 |  | In progress
|  | P2 |  | Blocked
|  | P3 |  | Completed

## Mechanical
Task | Subsystem | Priority (0 is highest) | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Wheel Design | Drivetrain | P2 | Jack Bailey | In progress | 2025-11-19 |  |  |  | prototype being manufactured
Rocker Bogie | Drivetrain | P0 | Kale Parnham | In progress | 2025-11-19 |  |  |  | Will need Aluminum after break
Articulated Arm | Arm Assembly | P1 | Tran Duy Linh Dinh | In progress | 2025-11-13 |  |  |  | Design work in progress
General Use Gripper | Arm Assembly | P2 | Natalie Jagger | In progress | 2025-11-19 |  |  |  | Design work in progress
Frame | Structure | P0 | Karen Jimenez | In progress
Electronics Box | Structure | P1 |  | Blocked |  |  |  |  | Need exact dimensions from electrical and position of diff gears from RB. Also need shape of structure

## Software
Task | Subsystem | Priority (0 is highest) | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Encoder sensor reading | Embedded Control | P0 |  | Not started
IMU sensor integration | Embedded Control | P1 |  | Not started
Temperature sensor reading | Embedded Control | P2 |  | Not started
Motor PWM control | Embedded Control | P3 |  | Not started
ROS 2 Architecture | Navigation |  | Youssef Gabriel Amazirh | In progress | 2025-11-25